## Backlog
Story ID | Old ID | Epic | Epic name | Story | Requirement | Story points | Sprint | Owner | GitHub username | Status | Branch / evidence
US-01 | US-07 | WBMME-1 | Data Workspace | Upload a CSV dataset | MLE-F-003 | 5 | Sprint 1 | Vikas (Member 4) | vikasvittalaihole | To Do
US-02 | US-08 | WBMME-1 | Data Workspace | Upload validation | MLE-SR-003 | 3 | Sprint 1 | Vikas (Member 4) | vikasvittalaihole | To Do
US-03 | US-09 | WBMME-1 | Data Workspace | Preview and profile a dataset | MLE-F-004 | 3 | Sprint 1 | Vikas (Member 4) | vikasvittalaihole | To Do
US-04 | US-10 | WBMME-1 | Data Workspace | Prepare data | MLE-F-005 | 5 | Sprint 1 | Vikas (Member 4) | vikasvittalaihole | To Do
US-05 | US-11 | WBMME-1 | Data Workspace | Configure train/test split | MLE-F-006 | 3 | Sprint 1 | Vikas (Member 4) | vikasvittalaihole | To Do
US-06 | US-13 | WBMME-2 | Model Training & Selection | Model catalogue | MLE-F-007 | 3 | Sprint 1 | Varnika (Member 2) | varnikasadineni | Done (pending PR review) | feature/us-06-model-catalogue ¦ 23 tests; 1 commit
US-07 | US-14 | WBMME-2 | Model Training & Selection | Set hyperparameters | MLE-F-008 | 5 | Sprint 1 | Varnika (Member 2) | varnikasadineni | Done (pending PR review) | feature/us-07-hyperparameters ¦ 52 tests (cumulative)
US-08 | US-15 | WBMME-2 | Model Training & Selection | Train as a background job | MLE-F-009 | 8 | Sprint 1 | Varnika (Member 2) | varnikasadineni | Done (pending PR review) | feature/us-08-background-training ¦ 95 tests (cumulative)
US-09 | US-16 | WBMME-2 | Model Training & Selection | Safe model artifacts | MLE-SR-004 | 3 | Sprint 1 | Tejas (Member 3) | TejasPonnappa | To Do
US-10 | US-19 | WBMME-3 | Evaluation & Explainability | Evaluation metrics | MLE-F-010 | 5 | Sprint 1 | Tejas (Member 3) | TejasPonnappa | To Do
US-11 | US-26 | WBMME-5 | Testing & Validation | Unit tests for core services | Test Plan 5 | 5 | Sprint 1 | Varnika (Member 2) | varnikasadineni | Done (pending PR review) | feature/us-11-unit-tests ¦ 139 tests (cumulative)
US-12 | US-31 | WBMME-6 | CI/CD, Security & Deployment | CI pipeline | Part-2 Sprint 1 | 5 | Sprint 1 | Soumya (Member 1) | KOTRASAISOUMYASRI | To Do
US-13 | US-35 | WBMME-7 | Final Documentation & Demonstration | Sprint 1 demo video | Part-2 Sprint 1 | 2 | Sprint 1 | Soumya (Member 1) | KOTRASAISOUMYASRI | To Do
US-14 | US-38 | WBMME-8 | Core Platform & Security | Django project skeleton | SAD 3.5, 3.6 | 3 | Sprint 1 | Soumya (Member 1) | KOTRASAISOUMYASRI | To Do
US-15 | US-39 | WBMME-8 | Core Platform & Security | Register and log in | MLE-F-001 | 5 | Sprint 1 | Tejas (Member 3) | TejasPonnappa | To Do
US-16 | US-40 | WBMME-8 | Core Platform & Security | Password hashing | MLE-SR-001 | 2 | Sprint 1 | Soumya (Member 1) | KOTRASAISOUMYASRI | To Do
US-17 | US-41 | WBMME-8 | Core Platform & Security | Role-based access | MLE-F-002 | 5 | Sprint 1 | Tejas (Member 3) | TejasPonnappa | To Do
US-18 | US-42 | WBMME-8 | Core Platform & Security | Sessions and login protection | MLE-SR-007 | 5 | Sprint 1 | Soumya (Member 1) | KOTRASAISOUMYASRI | To Do
US-19 | US-12 | WBMME-1 | Data Workspace | Upload speed target | MLE-NF-001 | 3 | Sprint 2 | Vikas (Member 4) | vikasvittalaihole | To Do
US-20 | US-17 | WBMME-2 | Model Training & Selection | Training speed target | MLE-NF-002 | 3 | Sprint 2 | Varnika (Member 2) | varnikasadineni | Done (pending PR review) | feature/us-20-training-speed ¦ 145 tests incl. 3 perf
US-21 | US-18 | WBMME-2 | Model Training & Selection | Contain failed jobs | MLE-NF-006 | 5 | Sprint 2 | Varnika (Member 2) | varnikasadineni | Done (pending PR review) | feature/us-21-contain-failed-jobs ¦ 158 tests (cumulative)
US-22 | US-20 | WBMME-3 | Evaluation & Explainability | Confusion matrix and metric chart | MLE-F-011 | 5 | Sprint 2 | Tejas (Member 3) | TejasPonnappa | To Do
US-23 | US-21 | WBMME-3 | Evaluation & Explainability | Feature importance | MLE-F-012 | 3 | Sprint 2 | Tejas (Member 3) | TejasPonnappa | To Do
US-24 | US-22 | WBMME-4 | Experiment Management & Reporting | Run history | MLE-F-013 | 5 | Sprint 2 | Vikas (Member 4) | vikasvittalaihole | To Do
US-25 | US-23 | WBMME-4 | Experiment Management & Reporting | Compare runs | MLE-F-014 | 5 | Sprint 2 | Vikas (Member 4) | vikasvittalaihole | To Do
US-26 | US-24 | WBMME-4 | Experiment Management & Reporting | Export results as CSV | MLE-F-015 | 3 | Sprint 2 | Vikas (Member 4) | vikasvittalaihole | To Do
US-27 | US-25 | WBMME-4 | Experiment Management & Reporting | History scale and pagination | MLE-NF-007 | 3 | Sprint 2 | Vikas (Member 4) | vikasvittalaihole | To Do
US-28 | US-27 | WBMME-5 | Testing & Validation | Integration and system tests | Test Plan 13 | 5 | Sprint 2 | Varnika (Member 2) | varnikasadineni | Done (pending PR review) | feature/us-28-integration-system-tests ¦ 202 tests (cumulative)
US-29 | US-28 | WBMME-5 | Testing & Validation | Security validation | MLE-SR-001 to 007 | 5 | Sprint 2 | Soumya (Member 1) | KOTRASAISOUMYASRI | To Do
US-30 | US-29 | WBMME-5 | Testing & Validation | Load test | MLE-NF-003 | 5 | Sprint 2 | Varnika (Member 2) | varnikasadineni | Done (pending PR review) | feature/us-30-load-test ¦ 202 tests; load test passed
US-31 | US-30 | WBMME-5 | Testing & Validation | Usability test | MLE-NF-005 | 3 | Sprint 2 | Tejas (Member 3) | TejasPonnappa | To Do
US-32 | US-32 | WBMME-6 | CI/CD, Security & Deployment | Docker build | MLE-NF-004 | 5 | Sprint 2 | Soumya (Member 1) | KOTRASAISOUMYASRI | To Do
US-33 | US-33 | WBMME-6 | CI/CD, Security & Deployment | HTTPS only | MLE-SR-002 | 3 | Sprint 2 | Soumya (Member 1) | KOTRASAISOUMYASRI | To Do
US-34 | US-34 | WBMME-6 | CI/CD, Security & Deployment | Security scan | Test Plan 5.1 | 3 | Sprint 2 | Soumya (Member 1) | KOTRASAISOUMYASRI | To Do
US-35 | US-36 | WBMME-7 | Final Documentation & Demonstration | Sprint 2 demo video | Part-2 Sprint 2 | 2 | Sprint 2 | Soumya (Member 1) | KOTRASAISOUMYASRI | To Do
US-36 | US-37 | WBMME-7 | Final Documentation & Demonstration | Final report and deviation log | Part-2 Sprint 2 | 3 | Sprint 2 | Soumya (Member 1) | KOTRASAISOUMYASRI | To Do
US-37 | US-43 | WBMME-8 | Core Platform & Security | Admin console | MLE-F-016 | 8 | Sprint 2 | Tejas (Member 3) | TejasPonnappa | To Do
US-38 | US-44 | WBMME-8 | Core Platform & Security | Ownership checks and audit log | MLE-SR-005 | 5 | Sprint 2 | Tejas (Member 3) | TejasPonnappa | To Do
US-39 | US-45 | WBMME-8 | Core Platform & Security | Request and job limits | MLE-SR-006 | 5 | Sprint 2 | Varnika (Member 2) | varnikasadineni | Done (pending PR review) | feature/us-39-request-and-job-limits ¦ 191 tests (cumulative)
Blue = input you may edit (story points). Epics renumbered WBMME-1 to WBMME-8 on 13 Oct 2026; stories renumbered US-01 to US-39 in sprint order, Sprint 1 first (Old ID column = the earlier US number, also the old GitHub title). Status values: To Do, In Progress, In Review, Done.

## Epics
Epic | Name | Old number | Stories | Points | Sprint 1 stories | Sprint 2 stories
WBMME-1 | Data Workspace | WBMME-4
WBMME-2 | Model Training & Selection | WBMME-5
WBMME-3 | Evaluation & Explainability | WBMME-6
WBMME-4 | Experiment Management & Reporting | WBMME-7
WBMME-5 | Testing & Validation | WBMME-8
WBMME-6 | CI/CD, Security & Deployment | WBMME-9
WBMME-7 | Final Documentation & Demonstration | WBMME-10
WBMME-8 | Core Platform & Security | WBMME-11
Total

## Sprint summary
Member | Sprint 1 stories | Sprint 1 points | Sprint 2 stories | Sprint 2 points | Total stories | Total points
Soumya (Member 1)
Varnika (Member 2)
Tejas (Member 3)
Vikas (Member 4)
Total
Minimum stories per sprint (from class) | 15
Sprint 1 meets the minimum?
Sprint 2 meets the minimum?
Assumption: 15 stories per sprint is the minimum the professor stated in class (13 Oct 2026).

## Owner changes
Story ID | Old ID | Story | Was | Now | GitHub username (new owner)
US-09 | US-16 | Safe model artifacts | Varnika (Member 2) | Tejas (Member 3) | TejasPonnappa
US-14 | US-38 | Django project skeleton | Tejas (Member 3) | Soumya (Member 1) | KOTRASAISOUMYASRI
US-16 | US-40 | Password hashing | Tejas (Member 3) | Soumya (Member 1) | KOTRASAISOUMYASRI
US-18 | US-42 | Sessions and login protection | Tejas (Member 3) | Soumya (Member 1) | KOTRASAISOUMYASRI
US-29 | US-28 | Security validation | Varnika (Member 2) | Soumya (Member 1) | KOTRASAISOUMYASRI
US-31 | US-30 | Usability test | Varnika (Member 2) | Tejas (Member 3) | TejasPonnappa
US-39 | US-45 | Request and job limits | Tejas (Member 3) | Varnika (Member 2) | varnikasadineni

## Removed
Old story ID | Story | Reason
US-06 | Record design deviations | Deviations are recorded in the final report and deviation log story; epic Architecture & Software Design (old WBMME-3) removed with it
US-01 | Repository, organisation and access | Done at the 13 Oct checkpoint; no product value
US-02 | Backlog and sprint plan | Done; the backlog itself is the deliverable
US-03 | Final SRS | Document already complete and merged
US-04 | Keep the traceability matrix current | Housekeeping; the RTM lives in the SRS, SAD and Test Plan
US-05 | Final SAD | Document already complete and merged
Kept although not code (required by the Part-2 guidelines): US-29 and US-30 demo videos (old US-35, US-36) and US-31 final report and deviation log (old US-37). Epics removed: old WBMME-1, WBMME-2 and WBMME-3. The removed stories are closed on GitHub with the prefix [Removed].